## Cover
INITIAL TUNING ACCEPTANCE CERTIFICATE
| Customer Name | PT. XL AXIATA TBK.
| Area | SUMATERA UTARA
| City | KAB. KARO
| DU ID SON | SUM-SU-KBJ-0106_WLUAL_MSE_L1800
| NE Name | 4222520E_LTE_UJUNG_AJI
| SOW | MS 4T6S (1800+2100)
| Technology | LTE 1800
| On Air Date | 2024-06-05
Acceptance Date
Site Location
2024

## General Site Information
1. General Site Information
| General Site Information |  |  | Remarks | [6 empty] | Site location | RSRP MR Discovery before site OA
| Tower ID |  |  | SUM-SU-KBJ-0106 |  |  |  | SUM-SU-KBJ-0106
| DU ID SON |  |  | SUM-SU-KBJ-0106_WLUAL_MSE_L1800 |  |  |  | SUM-SU-KBJ-0106_WLUAL_MSE_L1800
| Site ID |  |  | 4222520E |  |  |  | 4222520E
| Site Name |  |  | 4222520E_LTE_UJUNG_AJI |  |  |  | 4222520E_LTE_UJUNG_AJI
| Site Address |  |  | Jl. Ujung Aji No. 56 Desa Ujung Aji Kec. Berastagi - SUMUT
| Long / Lat |  |  | 98.52151111/3.171561111
| Azimuth |  |  | 65/ 110 /315
| Tilt (E/M) |  |  | (RET SN/2) (RET SN/1) (RET SN/1)
| Antenna Height |  |  | 38M
| RRU Type: Existing / Plan / Implemented |  |  | RF900: Existing-6xMRFU_V2 RF1800: New-1xRRU5866 + Existing-1xRRU5502+1xRRU5909 RF2100: New-1xRRU5866 + Existing-1xRRU5502+1xRRU5905
| SoW BoQ: Plan/Implemented |  |  | MS 4T6S (1800+2100)_Sec_2
| ALL System |  |  | GSM+L1800+L2100 |  |  |  | GSM+L1800+L2100
| Frequency Layer / EUARFCN / Bandwidth |  |  | L1800/1325/20Mhz |  |  |  | L1800/1325/20Mhz
| PCI information Sect 1 / Sect 2 / Sect 3 |  |  | 432/ 433/ 434 |  |  |  | 432/ 433/ 434
| TAC Configuration |  |  | 22039 |  |  |  | 22039
| Antenna Type / MIMO |  |  | Sector1 (2T2R)/ Sector 2&4(8T8R)/3 (4T4R)
| Area Class |  |  | Inner
| Sector | Site ID | ENodeB Name |  | Cell Name | Cell Index | PCI | Azimuth | M-Tilt | E-Tilt
| 1 | 4222520E | 4222520E_LTE_UJUNG_AJI |  | MD4G18_4222520E_4 | 4 | 432 | 65 | 2 | RET SN
| 2 | 4222520E | 4222520E_LTE_UJUNG_AJI |  | MD4G18_4222520E_5 | 5 | 433 | 110 | 1 | RET SN
| 3 | 4222520E | 4222520E_LTE_UJUNG_AJI |  | MD4G18_4222520E_6 | 6 | 434 | 315 | 1 | RET SN
| 4 | 4222520E | 4222520E_LTE_UJUNG_AJI |  | MD4G18_4222520E_25_M | 25 | 249 | 170 | 1 | RET SN
| 5 | 4222520E | 4222520E_LTE_UJUNG_AJI
| 6 | 4222520E | 4222520E_LTE_UJUNG_AJI
2024
2.4KM
2.5KM
1.5KM
2.4KM
3.2KM
2.3 KM
1.3 KM
Open Area
1.4 KM

## VDT View
2. VDT View
Dominant Cell
|  | Note : MDT 20^20 |  |  |  | Note : MDT 50^50
[5 empty] | Sectoral |  | Status
[5 empty] | Sector 1 |  | Match
[5 empty] | Sector 2 |  | Match
[5 empty] | Sector 3 |  | Match
[5 empty] | Sector 4 |  | Match
[5 empty] | Remark |  | PASS
| MD4G18_4222520E_4 |  | MD4G18_4222520E_5 |  |  |  |  | MD4G18_4222520E_6
MD4G18_4222520E_25_M
Virtual RSRP (Reference Signal Received Power)
| Before |  |  | After
Table sample polygon ISD 60%
[9 empty] | Range (dBm) | Colour | Sample |  | Percentage Sample
[11 empty] | Before | After | Before | After
[9 empty] | -40 to -85 |  | 24 | 31 | 24.49% | 28.7%
[9 empty] | -85 to -95 |  | 22 | 47 | 22.45% | 43.52%
[9 empty] | -95 to -100 |  | 29 | 21 | 29.59% | 19.44%
[9 empty] | -100 to -105 |  | 9 | 2 | 9.184% | 1.852%
[9 empty] | -105 to -110 |  | 10 | 5 | 10.2% | 4.63%
[9 empty] | -110 to -140 |  | 4 | 2 | 4.082% | 1.852%
[9 empty] | Total |  | 98 | 108 | 100% | 100%
[9 empty] | >=-105 Inner |  | 84 | 101 | 85.71% | 93.52%
7.804%
[9 empty] | BEFORE |  | AFTER |  | Remark
[9 empty] | 85.71% |  | 93.52% |  | 7.804% | Increased
[10 empty] | 85.71% | 93.52%
Virtual CQI
| Before |  |  | After
Table sample polygon ISD 60%
[9 empty] | Range | Colour | Sample |  | Percentage Sample
[11 empty] | Before | After | Before | After
[9 empty] | [10,15] |  | 50 | 66 | 60.98% | 69.47%
[9 empty] | [8.10] |  | 16 | 15 | 19.51% | 15.79%
[9 empty] | [5,8] |  | 13 | 14 | 15.85% | 14.74%
[9 empty] | [2,5] |  | 3 | 0 | 3.659% | 0%
[9 empty] | [0.2] |  | 0 | 0 | 0% | 0%
[9 empty] | Total |  | 82 | 95 | 100% | 100%
[9 empty] | >=8 |  | 66 | 81 | 80.49% | 85.26%
4.775%
[9 empty] | BEFORE |  | AFTER |  | Remark
[9 empty] | 80.49% |  | 85.26% |  | 4.775% | Increased
[10 empty] | 80.49% | 85.26%
Intra Freq Cell Relations
| MD4G18_4222520E_4 |  | MD4G18_4222520E_5 |  |  |  |  | MD4G18_4222520E_6
| MD4G18_4222520E_25_M |  | 0 |  |  |  |  | 0

## VDT KPI Summary
3. VDT KPI
[6 empty] | Before | After | [5 empty] | Remark
No | Test Item | KPI Source | Unit | Reference | 4G KPI Huawei | Baseline | Sec 1 | Sec 2 | Sec 3 | Sec 4 | Sec 5 | Sec 6
1 | Cross feeder Check | MDT | % | Per Sector | No Crossfeeder | NA | No Cross Feeder | No Cross Feeder | No Cross Feeder | No Cross Feeder | No Cross Feeder | No Cross Feeder | PASS
2 | DL Single User Throughput (Max – Best Spot) | MDT | Mbps | Per Sector | > 3 Mbps Per Sector | NA | 91.9851 | 81.8608 | 70.9512 | 70.9512 | 70.9512 | 70.9512 | PASS
3 | RSRP >-105dBm | MDT | % | Total Site | ISD 60% (L21 40%) Inner (-105 dBm) >= 90%, (L21: 80%) Outer (-110 dBm) >= 85%, (L21: 75%) For Rural (-110 dBm) >= 85%, (L21: 75%) ISD follow 80% TA | 85.71% | 93.52% | [5 empty] | PASS
4 | CQI>8 (RSRP >-105dBm) | MDT | % | Total Site | ISD 60% ≥75% (L21 ISD 40%) For Rural ISD follow 80% TA | 80.49% | 85.26% | [5 empty] | PASS
5 | Intra-Frequency Handover | MDT | % | Per Sector | ≥ 97% | NA | 99.63 | 99.76 | 99.78 | 99.78 | 99.78 | 99.78 | PASS
Crossfeeder partial check from U2020

## NMS KPI
4. NMS KPI
|  | Date Collection Before | 19 May 2024 - 21 May 2024
|  | Date Collection After | 2 Jun 2024 - 4 Jun 2024
| Core Cell_NMS KPI. 3 days measurement Period | [14 empty] | Data Before
| NMS KPI |  | Name | Target Baseline New NE | Measured On | Before Baseline | MD4G18_4222520E_4 | MD4G18_4222520E_5 | MD4G18_4222520E_6 | MD4G18_4222520E_25_M | 0 | 0 | Average Value | Status | Remarks | MD4G18_4223042E_4 | MD4G18_4223042E_5 | MD4G18_4223042E_6
| 4G RAN KPI | Availability | Network Element Availability (%) | > 98.5% | Cell Daily | 100 | 100 | 100 | 100 |  |  |  | 100 | PASS |  | 100 | 100 | 100
|  | Accessability | Session Setup Success Rate (%) | ≥ 99% | Avg Cell Busy Hour | 99.3366 | 98.6573 | 98.8601 | 98.8525 |  |  |  | 98.79 | PASS |  | 99.6721 | 98.7615 | 99.5761
|  |  | CSFB Success Rate | ≥ 97 | Cell Busy Hour | 100 | 100 | 100 | 100 |  |  |  | 100 | PASS |  | 100 | 100 | 100
|  |  | Voice Call Setup Success Rate (VoLTE) | ≥ 99 | Cell Busy Hour | 100 | 100 | 100 | 100 |  |  |  | 100 | PASS |  | 100 | 100 | 100
|  |  | CBRA Success Rate (%) | >=50 % (L900) >=75% (L1800 & L2100) | Avg Cell Busy Hour | 89.8935 | 92.9645 | 91.224 | 95.6553 |  |  |  | 93.2813 | PASS |  | 93.7349 | 77.7535 | 98.1922
|  | Retainability | Session Abnormal Release Rate (%) | ≤ 1.4% | Avg Cell Busy Hour | 0.24346 | 0.45287 | 0.271 | 0.1567 |  |  |  | 0.29352 | NOT PASS |  | 0.1225 | 0.4611 | 0.14677
|  |  | Handover Success Rate Intra-Inter Frequency (%) | ≥ 97% | Avg Cell Busy Hour | 99.1839 | 99.3709 | 98.6579 | 97.3105 |  |  |  | 98.4464 | PASS |  | 99.3769 | 98.4104 | 99.7644
|  | Integrity | DL Volume (Gigabyte) | Info Only | Cell Daily | 121.4815 | 53.3416 | 195.6778 | 106.6476 |  |  |  | 118.5556 | Info Only |  | 57.6543 | 203.4013 | 103.3889 | 0 | 0
|  |  | UL Volume (Gigabyte) | Info Only | Cell Daily | 11.8562 | 5.6496 | 18.4206 | 10.0428 |  |  |  | 11.371 | Info Only |  | 5.422 | 20.3841 | 9.7625 | 0 | 0
|  |  | Downlink Peak User Throughput (Mbps) | Info Only | Avg Cell Busy Hour | 0 | 46.5272 | 61.0458 | 83.9605 |  |  |  | 63.8445 | Info Only |  | 0 | 0 | 0
|  |  | Uplink User Throughput(PDCP) | Info Only | Cell Daily | 2.1346 | 1.7192 | 2.475 | 2.9289 |  |  |  | 2.3744 | Info Only |  | 1.5724 | 1.4233 | 3.4081
|  |  | Number Of RRC Connected User | Info Only | Cell Daily | 56.236 | 26.6524 | 75.6549 | 49.1305 |  |  |  | 50.4793 | Info Only |  | 28.4702 | 95.6246 | 44.6131 | - | -
|  |  | CQI | ≥ 8 | Cell Daily | 9.488 | 8.1954 | 9.6326 | 11.0975 |  |  |  | 9.6418 | PASS |  | 8.0143 | 9.1845 | 11.2652
|  | User Distribution | QPSK Distribution (%) | <45% <50% (L900) | Avg Cell Busy Hour | 42.1851 | 63.8964 | 24.9134 | 35.9421 |  |  |  | 41.584 | PASS |  | 71.4603 | 26.0892 | 29.0057 | - | -
|  |  | Timing Advance (ISD) | > 80% | Cell Measurement | 97.7167 | 97.5 | 100 | 95.65 |  |  |  | 97.7167 | PASS |  | 97.5 | 100 | 95.65
|  | Other | RSSI (PUCH) | ≤ -105 dBm | Cell Daily | -116.7604 | -116.7049 | -117.2292 | -115.8819 |  |  |  | -116.6053 | PASS |  | -117.4896 | -116.7014 | -116.0903 | - | -
|  |  | Far neighbor attempts 150 | Far neighbor attempts 150 (3 times ISD and exclude L900) | Cell Daily | 2222.8333 | - | 1467 | 0 |  |  |  | 733.5 | PASS |  | - | 4445.6667 | 0 | - | 0
|  |  | MIMO Transmission Rank=2 Rate | 35% For Add RRU and/or Antenna changes 20% For L900 and other | Cell Daily | 45.6657 | 37.0016 | 52.9097 | 56.492 |  |  |  | 48.8011 | PASS |  | 34.5896 | 44.5747 | 57.8329 | - | -
|  |  | SRVCC Success Rate | Info Only | Cell Busy Hour | - | - | - | - |  |  |  | - | Info Only |  | - | - | - | - | -
|  |  | VoLTE Traffic (Erl) | Info Only | Cell Daily | 0.063756 | 0.042767 | 0.1156 | 0.061467 |  |  |  | 0.073278 | Info Only |  | 0.069067 | 0.098567 | 0.023633
|  |  | VoLTE User | > 0 | Cell Daily | 0.0637 | 0.042833 | 0.1157 | 0.061567 |  |  |  | 0.073367 | PASS |  | 0.0691 | 0.098367 | 0.023633
|  |  | Voice Call Drop Rate (Volte) | ≤ 3 | Cell Daily | 0.091078 | 0 | 0.31153 | 0 |  |  |  | 0.10384 | NOT PASS |  | 0 | 0.27323 | 0
*KPI Info Only can't be subject for rejection
2024

## Timing Advance
5. Timing Advance
| Timing Advance Distribution | Timing Advance Neighbor Cell (Info Only)
2024
Sector 3 -> 1.3 KM -> 95.65%
Sector 2 -> Open Area -> 100.00%
Sector 1 -> 2.3 KM -> 97.50%
Sector 2 -> Open Area-> 100.00%
Sector 2 -> 1.3 KM -> 96.19%
Sector 2 -> 2.3 KM -> 94.61%
Sector 1 -> 1.3 KM -> 98.96%
Sector 2 -> 1.1 KM -> 61.47%
Sector 4 -> 1.3 KM -> 55.76%
Sector 1 -> 1.3 KM -> 98.96%
Sector 5 -> 1.3 KM -> 55.76%

## ATP Document
7. ATP Document Attachment
2024

## Justification
6. Justification
| KPI | Finding Issue |  | Remark
| NMS and VDT already Pass | RSRP improve and CQI improve RSRP Before 85.71%, After 93.52%, Improve 7.80% CQI Before 80.49%, After 85.26%, Improve 4.78% |  | Done visit site SUM-SU-KBJ-0106_WLUAL_MSE_L1800_IT 4222520E_LTE_UJUNG_AJI Date : 07 June 2024 AZ : 65/155/315 > 65/140/315 MT :2/0/1 > 2/1/1 ET : RET 20 / RET 20 / RET 20 Height Antenna : 41 M Antenna Type :Sect 1&3 =ATR4518R6v07, Sect 2= A08260PD05v06
| RSRP MDT 20^20 |  |  | RSRP MDT 50^50
| CQI MDT 20^20 |  |  | CQI MDT 50^50
MOD 3 Collosion Clear
PCI
Population
Payload & User Site Level
Payload & User Site Level Comparison
Payload & User Cluster Level
Payload & User Cluster Level Comparison
PRB Utilasi
| Sector 2 All |  | Sector 2 existing
TA NPM WEEK25
MD4G18_4222520E_4 |  |  | MD4G18_4222520E_5 |  |  | MD4G18_4222520E_6
MD4G18_4222520E_25_M |  |  | 0 |  | 0
Sector 2 MSE
ITR
before
after

## Optimization Tracker
Activity | [7 empty] | Before | [8 empty] | After | [8 empty] | Parameter Action | Result
[8 empty] | Azimuth |  |  | Mech Tilt |  |  | E Tilt |  |  | Azimuth |  |  | Mech Tilt |  |  | E Tilt
Type of Site | Tower ID | DU ID Father | DU ID Son | RF SOW | Date | Issue | Root Cause | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Macro | SUM-SU-KBJ-0106 | SUM-SU-KBJ-0106_WLUAL | SUM-SU-KBJ-0106_WLUAL_MSE_L1800 | IT & OSS | 7 Juni 2024 |  |  | 65 | 155 | 315 | 2 | 0 | 1 | RET | RET | RET | 65 | 140 | 315 | 2 | 1 | 1 | RET | RET | RET

## INFO
Info
1 | GE 1st Tier | OK | [5 empty] | ✅
2 | PAYLOAD Cluster | Improve | [5 empty] | ✅
3 | PAYLOAD Site Level | Improve | [5 empty] | ✅
4 | PCI Homogen | OK | [5 empty] | ✅
5 | PRB | SOW Balance | [5 empty] | ✅
6 | RANK2 | Sector SOW Improve | [5 empty] | ✅
7 | PORT UNBALANCE | Balance | Info only |  |  |  |  | ✅
8 | ATP | ATP Approved | Info only |  |  |  |  | ✅
9 | MR RSRP | Increased | 7.804% | from | 85.71% | to | 93.52% | ✅
10 | MR CQI | Increased | 4.775% | from | 80.49% | to | 85.26% | ✅
11 | TA Overshoot | safe >80% | [5 empty] | ✅
12 | ALARM | OK | [5 empty] | ✅
13 | VSWR | Clear | [5 empty] | ✅
14 | CRS PORT | 4 Port | [5 empty] | ✅
15 | LICENSE | Clear | [5 empty] | ✅
16 | PCI MOD3 | Clear | [5 empty] | ✅
17 | Capture review CO NPM | [6 empty] | ❌
1. RET Info
2. Capture Active Alarm
3. Capture VSWR Setting
4. LTE Bandwidth and MIMO Config
5. Power Info
6. All KPI
8. DSP ETHPORT

## Conclusion & Remarks
8. Conclusion & Remarks
| We Summarize that |  |  |  | 4222520E_LTE_UJUNG_AJI |  |  |  | meets below KPI score:
|  |  |  | KPI Category |  | All | Pass | Fail | Percentage
|  |  |  | Driveless KPI |  | 5 | 5 | 0 | 100%
|  |  |  | NMS KPI |  | 15 | 13 | 2 | 86.67%
|  | We conclude that |  |  | 4222520E_LTE_UJUNG_AJI |  |  |  | is:
Pass, without note
Pass, without note
Not pass
with remark as follows :
Remarks :
2024