## Cover
INITIAL TUNING ACCEPTANCE CERTIFICATE
| Customer Name | PT. XL AXIATA TBK.
| Area | ACEH
| City | KOTA LHOKSEUMAWE
| DU ID SON | SUM-AC-LSM-0131_WLUAL_R4T_L1800
| NE Name | 4214270E_LTE_Poltek Lhokseumawe
| SOW | Upgrade 4T4R (1800+2100)
| Technology | LTE 1800
| On Air Date | 2024-06-05
Acceptance Date
Site Location
2024

## General Site Information
1. General Site Information
| General Site Information |  |  | Remarks | [6 empty] | Site location | RSRP MR Discovery before site OA
| Tower ID |  |  | SUM-AC-LSM-0131 |  |  |  | SUM-AC-LSM-0131
| DU ID SON |  |  | SUM-AC-LSM-0131_WLUAL_R4T_L1800 |  |  |  | SUM-AC-LSM-0131_WLUAL_R4T_L1800
| Site ID |  |  | 4214270E |  |  |  | 4214270E
| Site Name |  |  | 4214270E_LTE_Poltek Lhokseumawe |  |  |  | 4214270E_LTE_Poltek Lhokseumawe
| Site Address |  |  | Gempong Meunasah Masjid Puenteut, Kec. Blang Mangat, Kota Lhoksumawe, NAD
| Long / Lat |  |  | 97.15961111/5.121333333
| Azimuth |  |  | 140/ 245 /310
| Tilt (E/M) |  |  | (RET SN/4) (RET SN/3) (RET SN/4)
| Antenna Height |  |  | 43M
| RRU Type: Existing / Plan / Implemented |  |  | RF900: Existing-3xRRU5909 RF1800: New-1xRRU5866 - Sharing RRU + Existing-1xRRU3959 RF2100: New-1xRRU5866 - Sharing RRU + Existing-1xRRU5905
| SoW BoQ: Plan/Implemented |  |  | Upgrade 4T4R (1800+2100)_Sec_1&2
| ALL System |  |  | GSM+L1800+L2100 |  |  |  | GSM+L1800+L2100
| Frequency Layer / EUARFCN / Bandwidth |  |  | L1800/1325/20Mhz |  |  |  | L1800/1325/20Mhz
| PCI information Sect 1 / Sect 2 / Sect 3 |  |  | 409/ 408/ 410 |  |  |  | 409/ 408/ 410
| TAC Configuration |  |  | 21007 |  |  |  | 21007
| Antenna Type / MIMO |  |  | Sector1 (4T4R)/ Sector 2&3 (2T2R)
| Area Class |  |  | Inner
| Sector | Site ID | ENodeB Name |  | Cell Name | Cell Index | PCI | Azimuth | M-Tilt | E-Tilt
| 1 | 4214270E | 4214270E_LTE_Poltek Lhokseumawe |  | AC4G18_4214270E_4 | 4 | 409 | 140 | 4 | RET SN
| 2 | 4214270E | 4214270E_LTE_Poltek Lhokseumawe |  | AC4G18_4214270E_5 | 5 | 408 | 245 | 3 | RET SN
| 3 | 4214270E | 4214270E_LTE_Poltek Lhokseumawe |  | AC4G18_4214270E_6 | 6 | 410 | 310 | 4 | RET SN
2024
Open Area
3.2 KM
1.1 KM

## VDT View
2. VDT View
Dominant Cell
|  | Note : MDT 20^20 |  |  |  | Note : MDT 50^50
|  |  |  | Sectoral | Status
|  |  |  | Sector 1 | Match
|  |  |  | Sector 2 | Match
|  |  |  | Sector 3 | Match
|  |  |  | Remark | PASS
| AC4G18_4214270E_4 |  | AC4G18_4214270E_5 |  |  |  | AC4G18_4214270E_6
Virtual RSRP (Reference Signal Received Power)
| Before |  |  | After
Table sample polygon ISD 60%
[8 empty] | Range (dBm) | Colour | Sample |  | Percentage Sample
[10 empty] | Before | After | Before | After
[8 empty] | -40 to -85 |  | 186 | 216 | 25.44% | 24.55%
[8 empty] | -85 to -95 |  | 343 | 377 | 46.92% | 42.84%
[8 empty] | -95 to -100 |  | 78 | 134 | 10.67% | 15.23%
[8 empty] | -100 to -105 |  | 63 | 89 | 8.618% | 10.11%
[8 empty] | -105 to -110 |  | 49 | 53 | 6.703% | 6.023%
[8 empty] | -110 to -140 |  | 12 | 11 | 1.642% | 1.25%
[8 empty] | Total |  | 731 | 880 | 100% | 100%
[8 empty] | >=-105 Inner |  | 670 | 816 | 91.66% | 92.73%
-92.73%
[8 empty] | BEFORE |  | AFTER |  | Remark
[8 empty] | 91.66% |  | 92.73% |  | 1.072% | Maintained
[10 empty] | 91.66% | 92.73% | 1.072%
Virtual CQI
| Before |  |  | After
Table sample polygon ISD 60%
[8 empty] | Range | Colour | Sample |  | Percentage Sample
[10 empty] | Before | After | Before | After
[8 empty] | [10,15] |  | 226 | 331 | 33.73% | 40.42%
[8 empty] | [8.10] |  | 209 | 213 | 31.19% | 26.01%
[8 empty] | [5,8] |  | 200 | 232 | 29.85% | 28.33%
[8 empty] | [2,5] |  | 33 | 39 | 4.925% | 4.762%
[8 empty] | [0.2] |  | 2 | 4 | 0.2985% | 0.4884%
[8 empty] | Total |  | 670 | 819 | 100% | 100%
[8 empty] | >=8 |  | 435 | 544 | 64.93% | 66.42%
66.42%
[8 empty] | BEFORE |  | AFTER |  | Remark
[8 empty] | 64.93% |  | 66.42% |  | 1.497% | Maintained
[10 empty] | 64.93% | 66.42% | 1.497%
Intra Freq Cell Relations
| AC4G18_4214270E_4 |  | AC4G18_4214270E_5 |  |  |  | AC4G18_4214270E_6

## VDT KPI Summary
3. VDT KPI
[6 empty] | Before | After |  |  | Remark
No | Test Item | KPI Source | Unit | Reference | 4G KPI Huawei | Baseline | Sec 1 | Sec 2 | Sec 3
1 | Cross feeder Check | MDT | % | Per Sector | No Crossfeeder | NA | No Cross Feeder | No Cross Feeder | No Cross Feeder | PASS
2 | DL Single User Throughput (Max – Best Spot) | MDT | Mbps | Per Sector | > 3 Mbps Per Sector | NA | 91.9851 | 81.8608 | 70.9512 | PASS
3 | RSRP >-105dBm | MDT | % | Total Site | ISD 60% (L21 40%) Inner (-105 dBm) >= 90%, (L21: 80%) Outer (-110 dBm) >= 85%, (L21: 75%) For Rural (-110 dBm) >= 85%, (L21: 75%) ISD follow 80% TA | 91.66% | 92.73% |  |  | PASS
4 | CQI>8 (RSRP >-105dBm) | MDT | % | Total Site | ISD 60% ≥75% (L21 ISD 40%) For Rural ISD follow 80% TA | 64.93% | 66.42% |  |  | PASS
5 | Intra-Frequency Handover | MDT | % | Per Sector | ≥ 97% | NA | 99.63 | 99.76 | 99.78 | PASS
Crossfeeder partial check from U2020

## NMS KPI
4. NMS KPI
|  | Date Collection Before | 24 May 2024 - 26 May 2024
|  | Date Collection After | 5 Jun 2024 - 7 Jun 2024
| Core Cell_NMS KPI. 3 days measurement Period | [11 empty] | Data Before
| NMS KPI |  | Name | Target Baseline New NE | Measured On | Before Baseline | AC4G18_4214270E_4 | AC4G18_4214270E_5 | AC4G18_4214270E_6 | Average Value | Status | Remarks | MD4G18_4223042E_4 | MD4G18_4223042E_5 | MD4G18_4223042E_6
| 4G RAN KPI | Availability | Network Element Availability (%) | > 98.5% | Cell Daily | 99.5947 | 100 | 100 | 100 | 100 | PASS |  | 99.5947 | 99.5947 | 99.5947
|  | Accessability | Session Setup Success Rate (%) | ≥ 99% | Avg Cell Busy Hour | 99.6025 | 99.7611 | 99.7881 | 99.4605 | 99.6699 | PASS |  | 99.4411 | 99.5882 | 99.7783
|  |  | CSFB Success Rate | ≥ 97 | Cell Busy Hour | 101.2821 | 100 | 116.6667 | 100.9009 | 105.8559 | PASS |  | 102.5641 | 101.2821 | 100
|  |  | Voice Call Setup Success Rate (VoLTE) | ≥ 99 | Cell Busy Hour | 100 | 100 | 100 | 100 | 100 | PASS |  | 100 | 100 | 100
|  |  | CBRA Success Rate (%) | >=50 % (L900) >=75% (L1800 & L2100) | Avg Cell Busy Hour | 93.1846 | 96.4267 | 95.9179 | 92.7739 | 95.0395 | PASS |  | 87.9767 | 93.8104 | 97.7666
|  | Retainability | Session Abnormal Release Rate (%) | ≤ 1.4% | Avg Cell Busy Hour | 0.14132 | 0.034367 | 0.03 | 0.10753 | 0.0573 | PASS |  | 0.24407 | 0.1485 | 0.0314
|  |  | Handover Success Rate Intra-Inter Frequency (%) | ≥ 97% | Avg Cell Busy Hour | 98.7705 | 99.3406 | 99.6032 | 99.5171 | 99.4869 | PASS |  | 98.2256 | 98.7081 | 99.3777
|  | Integrity | DL Volume (Gigabyte) | Info Only | Cell Daily | 105.7366 | 90.1272 | 35.4332 | 181.0115 | 102.1907 | Info Only |  | 79.568 | 128.7449 | 108.8967
|  |  | UL Volume (Gigabyte) | Info Only | Cell Daily | 11.4427 | 10.6252 | 2.7586 | 23.1481 | 12.1773 | Info Only |  | 9.1675 | 14.9085 | 10.2521
|  |  | Downlink Peak User Throughput (Mbps) | Info Only | Avg Cell Busy Hour | 61.7874 | 70.9396 | 72.7857 | 36.3273 | 60.0175 | Info Only |  | 83.6385 | 33.858 | 67.8657
|  |  | Uplink User Throughput(PDCP) | Info Only | Cell Daily | 2.0063 | 2.7975 | 2.6458 | 1.6448 | 2.3627 | Info Only |  | 2.0894 | 1.2418 | 2.6878
|  |  | Number Of RRC Connected User | Info Only | Cell Daily | 50.3951 | 45.366 | 14.0874 | 91.6612 | 50.3715 | Info Only |  | 43.9046 | 68.9142 | 38.3666
|  |  | CQI | ≥ 8 | Cell Daily | 9.104 | 10.4151 | 11.4241 | 7.3094 | 9.7162 | PASS |  | 10.515 | 7.8592 | 8.9379
|  | User Distribution | QPSK Distribution (%) | <45% <50% (L900) | Avg Cell Busy Hour | 52.5898 | 48.9179 | 22.0864 | 42.6556 | 37.8866 | PASS |  | 58.1371 | 58.439 | 41.1932
|  |  | Timing Advance (ISD) | > 80% | Cell Measurement | #DIV/0! |  |  |  | #DIV/0! | #DIV/0!
|  | Other | RSSI (PUCH) | ≤ -105 dBm | Cell Daily | -118.7562 | -119.1354 | -117.1767 | -118.5868 | -118.2996 | PASS |  | -119.0104 | -118.213 | -119.0451
|  |  | Far neighbor attempts 150 | Far neighbor attempts 150 (3 times ISD and exclude L900) | Cell Daily | 0.66667 | 2.3333 | 1 | 0 | 1.1111 | NOT PASS |  | 2 | 0 | 0
|  |  | MIMO Transmission Rank=2 Rate | 35% For Add RRU and/or Antenna changes 20% For L900 and other | Cell Daily | 42.4437 | 52.8272 | 68.8253 | 27.2314 | 49.628 | PASS |  | 56.9671 | 29.9486 | 40.4154
|  |  | SRVCC Success Rate | Info Only | Cell Busy Hour | - | - | - | - | - | Info Only |  | - | - | -
|  |  | VoLTE Traffic (Erl) | Info Only | Cell Daily | 0.18903 | 0.3294 | 0.0825 | 0.35 | 0.25397 | Info Only |  | 0.24137 | 0.201 | 0.12473
|  |  | VoLTE User | > 0 | Cell Daily | 0.18943 | 0.3297 | 0.0825 | 0.35023 | 0.25414 | PASS |  | 0.24163 | 0.20183 | 0.12483
|  |  | Voice Call Drop Rate (Volte) | ≤ 3 | Cell Daily | 0 | 0 | 0 | 0 | 0 | PASS |  | 0 | 0 | 0
*KPI Info Only can't be subject for rejection
2024

## Timing Advance
5. Timing Advance
| Timing Advance Distribution | Timing Advance Neighbor Cell (Info Only)
2024
Sector 3 -> 1.1 KM -> 59.59%
Sector 2 -> 3.2 KM -> 100.00%
Sector 1 -> 3.2 KM -> 98.46%
Sector 2 -> 3.2 KM -> 100.00%
Sector 2 -> 1.1 KM -> 61.47%
Sector 3 -> 3.2 KM -> 99.31%

## ATP Document
7. ATP Document Attachment
2024

## Justification
6. Justification
| KPI | Finding Issue |  | Remark
| NMS and VDT already Pass | RSRP improve and CQI improve RSRP Before 40.76%, After 65.37%, Improve 24.61% CQI Before 59.37%, After 74.67%, Improve 15.30%
| RSRP MDT 20^20 |  |  | RSRP MDT 50^50
| CQI MDT 20^20 |  |  | CQI MDT 50^50
MOD 3 Collosion Clear
PCI
Population
TA NPM WEEK34
AC4G18_4214270E_4 |  |  | AC4G18_4214270E_5 |  | AC4G18_4214270E_6

## Optimization Tracker
Activity | [7 empty] | Before | [8 empty] | After | [8 empty] | Parameter Action | Result
[8 empty] | Azimuth |  |  | Mech Tilt |  |  | E Tilt |  |  | Azimuth |  |  | Mech Tilt |  |  | E Tilt
Type of Site | Tower ID | DU ID Father | DU ID Son | RF SOW | Date | Issue | Root Cause | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Macro | SUM-AC-LSM-0131 | SUM-AC-LSM-0131_WLUAL | SUM-AC-LSM-0131_WLUAL_R4T_L1800 | IT & OSS |  |  |  | 140 | 245 | 310 | 4 | 3 | 4 | 2 | 2 | 2 | 50 | 210 | 280 | 3 | 4 | 2 | RET | RET | RET

## INFO
Info
1 | GE 1st Tier | OK | [5 empty] | ✅
2 | PAYLOAD Cluster | Improve | [5 empty] | ✅
3 | PAYLOAD Site Level | Improve | [5 empty] | ✅
4 | PCI Homogen | OK | [5 empty] | ✅
5 | PRB | SOW Balance | [5 empty] | ✅
6 | RANK2 | Sector SOW Improve | [5 empty] | ✅
7 | PORT UNBALANCE | Balance | Info only |  |  |  |  | ✅
8 | ATP | ATP Approved | Info only |  |  |  |  | ✅
9 | MR RSRP | Maintained | 1.072% | from | 91.66% | to | 92.73% | ✅
10 | MR CQI | Maintained | 1.497% | from | 64.93% | to | 66.42% | ✅
11 | TA Overshoot | safe >80% | [5 empty] | ✅
12 | ALARM | OK | [5 empty] | ✅
13 | VSWR | Clear | [5 empty] | ✅
14 | CRS PORT | 4 Port | [5 empty] | ✅
15 | LICENSE | Clear | [5 empty] | ✅
16 | PCI MOD3 | Clear | [5 empty] | ✅
17 | Capture review CO NPM | [6 empty] | ❌
1. RET Info
2. Capture Active Alarm
3. Capture VSWR Setting
4. LTE Bandwidth and MIMO Config
5. Power Info
6. DSP ETHPORT
7. TA ISD
8. All KPI
Payload & User Site Level
Check Point
1. GE 1st Tier ✅ OK
2. PAYLOAD Cluster ❌ Degrade -2.24%
3. PAYLOAD Site Level ✅ Improve 4.77%
4. PCI Homogen ✅
5. PRB ✅ SOW Balance
6. RANK2 ✅ Sector SOW Improve
7. PORT UNBALANCE ✅ balance (Info Only)
8. ATP ✅ ATP Approved (Info Only)
9. MR RSRP ✅ Improve 4.36% from 89.31% to 93.67%
10. MR CQI ✅ improve 5.36% from 65.77% to 71.13%
11. TA Overshoot ✅ safe >80%
12. ALARM ✅ NOK
13. VSWR ✅ clear
14. CRS PORT ✅ 4ports
15. LICENSE ✅ clear
16. PCI MOD3 ✅ clear
17. Capture review CO NPM ❌
Audit
Before
After
Integrasi

## Conclusion & Remarks
8. Conclusion & Remarks
| We Summarize that |  |  |  | 4214270E_LTE_Poltek Lhokseumawe |  |  |  | meets below KPI score:
|  |  |  | KPI Category |  | All | Pass | Fail | Percentage
|  |  |  | Driveless KPI |  | 5 | 5 | 0 | 100%
|  |  |  | NMS KPI |  | 15 | 13 | 1 | 86.67%
|  | We conclude that |  |  | 4214270E_LTE_Poltek Lhokseumawe |  |  |  | is:
Pass, without note
Pass, without note
Not pass
with remark as follows :
Remarks :
2024