## Cover
INITIAL TUNING ACCEPTANCE CERTIFICATE
| Customer Name | PT. XL AXIATA TBK.
| Area | ACEH
| City | KOTA LHOKSEUMAWE
| DU ID SON | SUM-AC-LSM-0131_WLUAL_R4T_L1800
| NE Name | 4214270E_LTE_Poltek Lhokseumawe
| SOW | Upgrade 4T4R (1800+2100)
| Technology | LTE 1800
| On Air Date | 2024-06-05
Acceptance Date
Site Location
2024

## General Site Information
1. General Site Information
| General Site Information |  |  | Remarks | [6 empty] | Site location | RSRP MR Discovery before site OA
| Tower ID |  |  | SUM-AC-LSM-0131 |  |  |  | SUM-AC-LSM-0131
| DU ID SON |  |  | SUM-AC-LSM-0131_WLUAL_R4T_L1800 |  |  |  | SUM-AC-LSM-0131_WLUAL_R4T_L1800
| Site ID |  |  | 4214270E |  |  |  | 4214270E
| Site Name |  |  | 4214270E_LTE_Poltek Lhokseumawe |  |  |  | 4214270E_LTE_Poltek Lhokseumawe
| Site Address |  |  | Gempong Meunasah Masjid Puenteut, Kec. Blang Mangat, Kota Lhoksumawe, NAD
| Long / Lat |  |  | 97.15961111/5.121333333
| Azimuth |  |  | 140/ 245 /310
| Tilt (E/M) |  |  | (RET SN/4) (RET SN/3) (RET SN/4)
| Antenna Height |  |  | 43M
| RRU Type: Existing / Plan / Implemented |  |  | RF900: Existing-3xRRU5909 RF1800: New-1xRRU5866 - Sharing RRU + Existing-1xRRU3959 RF2100: New-1xRRU5866 - Sharing RRU + Existing-1xRRU5905
| SoW BoQ: Plan/Implemented |  |  | Upgrade 4T4R (1800+2100)_Sec_1&2
| ALL System |  |  | GSM+L1800+L2100 |  |  |  | GSM+L1800+L2100
| Frequency Layer / EUARFCN / Bandwidth |  |  | L1800/1325/20Mhz |  |  |  | L1800/1325/20Mhz
| PCI information Sect 1 / Sect 2 / Sect 3 |  |  | 409/ 408/ 410 |  |  |  | 409/ 408/ 410
| TAC Configuration |  |  | 21007 |  |  |  | 21007
| Antenna Type / MIMO |  |  | Sector1 (4T4R)/ Sector 2&3 (2T2R)
| Area Class |  |  | Inner
| Sector | Site ID | ENodeB Name |  | Cell Name | Cell Index | PCI | Azimuth | M-Tilt | E-Tilt
| 1 | 4214270E | 4214270E_LTE_Poltek Lhokseumawe |  | AC4G18_4214270E_4 | 4 | 409 | 140 | 4 | RET SN
| 2 | 4214270E | 4214270E_LTE_Poltek Lhokseumawe |  | AC4G18_4214270E_5 | 5 | 408 | 245 | 3 | RET SN
| 3 | 4214270E | 4214270E_LTE_Poltek Lhokseumawe |  | AC4G18_4214270E_6 | 6 | 410 | 310 | 4 | RET SN
2024
Open Area
3.2 KM
1.1 KM

## VDT View
2. VDT View
Dominant Cell
| Note : MDT 20^20 | [7 empty] | Note : MDT 50^50
|  | Sectoral |  |  |  | Status
|  | Sector 1 |  |  |  | Match
|  | Sector 2 |  |  |  | Match
|  | Sector 3 |  |  |  | Match
|  | Remark |  |  |  | PASS
| AC4G18_4214270E_4 |  | AC4G18_4214270E_5 |  |  |  |  | AC4G18_4214270E_6
Virtual RSRP (Reference Signal Received Power)
Table sample polygon ISD 60%
|  |  |  | Range (dBm) | Colour | Sample | Percentage Sample
|  |  |  | -40 to -85 |  | 2 | 2.532%
|  |  |  | -85 to -95 |  | 5 | 6.329%
|  |  |  | -95 to -100 |  | 0 | 0%
|  |  |  | -100 to -105 |  | 10 | 12.66%
|  |  |  | -105 to -110 |  | 20 | 25.32%
|  |  |  | -110 to -140 |  | 42 | 53.16%
|  |  |  | Total |  | 79 | 100%
|  |  |  | >=-105 Inner |  | 17 | 21.52%
Virtual CQI
Table sample polygon ISD 60%
|  |  |  | Range | Colour | Sample | Percentage Sample
|  |  |  | [10,15] |  | 36 | 55.38%
|  |  |  | [8.10] |  | 15 | 23.08%
|  |  |  | [5,8] |  | 11 | 16.92%
|  |  |  | [2,5] |  | 1 | 1.538%
|  |  |  | [0.2] |  | 2 | 3.077%
|  |  |  | Total |  | 65 | 100%
|  |  |  | >=8 |  | 51 | 78.46%
Intra Freq Cell Relations
| AC4G18_4214270E_4 |  | AC4G18_4214270E_5 |  |  |  |  | AC4G18_4214270E_6
1.950 Km
1.950 Km

## VDT KPI Summary
3. VDT KPI
[6 empty] | After |  |  | Remark
No | Test Item | KPI Source | Unit | Reference | 4G KPI Huawei | Sec 1 | Sec 2 | Sec 3
1 | Cross feeder Check | MDT | % | Per Sector | No Crossfeeder | No Cross Feeder | No Cross Feeder | No Cross Feeder | PASS
2 | DL Single User Throughput (Max – Best Spot) | MDT | Mbps | Per Sector | > 3 Mbps Per Sector | 91.9851 | 81.8608 | 70.9512 | PASS
3 | RSRP >-105dBm | MDT | % | Total Site | ISD 60% (L21 40%) Inner (-105 dBm) >= 90%, (L21: 80%) Outer (-110 dBm) >= 85%, (L21: 75%) For Rural (-110 dBm) >= 85%, (L21: 75%) ISD follow 80% TA | 21.52% |  |  | NOT PASS
4 | CQI>8 (RSRP >-105dBm) | MDT | % | Total Site | ISD 60% ≥75% (L21 ISD 40%) For Rural ISD follow 80% TA | 78.46% |  |  | PASS
5 | Intra-Frequency Handover | MDT | % | Per Sector | ≥ 97% | 99.63 | 99.76 | 99.78 | PASS
Crossfeeder partial check from U2020

## NMS KPI
4. NMS KPI
|  | Date Collection | 18 Sep 2024 - 20 Sep 2024 | L900
Core Cell_NMS KPI. 3 days measurement Period
| NMS KPI |  | Name | Target Baseline New NE | Measured On | PD4G09_4259747E9_1 | PD4G09_4259747E9_2 | PD4G09_4259747E9_3 | Average Value | Status | Remarks
| 4G RAN KPI | Availability | Network Element Availability (%) | > 98.5% | Cell Daily | 99.9865 | 100 | 100 | 100 | PASS
|  | Accessability | Session Setup Success Rate (%) | ≥ 99% | Avg Cell Busy Hour | 99.7398 | 99.2155 | 99.5427 | 98.3333 | NOT PASS | With Justification
|  |  | CSFB Success Rate | ≥ 97 | Cell Busy Hour | 100 | 100 | 100 | 100 | PASS
|  |  | Voice Call Setup Success Rate (VoLTE) | ≥ 99 | Cell Busy Hour | 100 | 100 | 100 | 100 | PASS
|  |  | CBRA Success Rate (%) | >=50 % (L900) >=75% (L1800 & L2100) | Avg Cell Busy Hour | 84.7883 | 44.6987 | 71.9962 | 67.412 | PASS | With Justification
|  | Retainability | Session Abnormal Release Rate (%) | ≤ 1.4% | Avg Cell Busy Hour | 0.53385 | 0.6162 | 4.4347 | 1.3826 | PASS
|  |  | Handover Success Rate Intra-Inter Frequency (%) | ≥ 97% | Avg Cell Busy Hour | 99.3903 | 99.2957 | 93.4454 | 98.9248 | PASS
|  | Integrity | DL Volume (Gigabyte) | Info Only | Cell Daily | 4.1279 | 5.0529 | 11.7671 | 1.3118 | Info Only
|  |  | UL Volume (Gigabyte) | Info Only | Cell Daily | 0.39803 | 0.6331 | 1.4563 | 0.25467 | Info Only
|  |  | Downlink Peak User Throughput (Mbps) | Info Only | Avg Cell Busy Hour | 44.76 | 11.6897 | 11.5488 | 7.3594 | Info Only
|  |  | Uplink User Throughput(PDCP) | Info Only | Cell Daily | 0.6189 | 0.6634 | 0.78293 | 0.5999 | Info Only
|  |  | Number Of RRC Connected User | Info Only | Cell Daily | 2.4056 | 2.535 | 6.7992 | 0.7774 | Info Only
|  |  | CQI | ≥ 8 | Cell Daily | 10.0938 | 7.6186 | 8.3686 | 6.7328 | NOT PASS | With Justification
|  | User Distribution | QPSK Distribution (%) | <45% <50% (L900) | Avg Cell Busy Hour | 64.8303 | 55.4888 | 37.7412 | 62.3099 | NOT PASS | With Justification
|  |  | Timing Advance (ISD) | > 80% | Cell Measurement | 100 | 93.27 | 100 | 97.7567 | PASS
|  | Other | RSSI (PUCH) | ≤ -105 dBm | Cell Daily | -119.0348 | -117.9259 | -116.4403 | -117.2285 | PASS
|  |  | Far neighbor attempts 150 | Far neighbor attempts 150 (3 times ISD and exclude L900) | Cell Daily | 0 | 0 | 0 | 0 | PASS
|  |  | MIMO Transmission Rank=2 Rate | 35% For Add RRU and/or Antenna changes 20% For L900 and other | Cell Daily | 49.6002 | 25.9512 | 25.0591 | 21.5769 | PASS
|  |  | SRVCC Success Rate | Info Only | Cell Busy Hour | - | - | - | - | Info Only
|  |  | VoLTE Traffic (Erl) | Info Only | Cell Daily | 0.0257 | 0.014267 | 0.042467 | 0.0279 | PASS
|  |  | VoLTE User | > 0 | Cell Daily | 0.0257 | 0.014267 | 0.042567 | 0.027933 | PASS
|  |  | Voice Call Drop Rate (Volte) | ≤ 3 | Cell Daily | 0 | 0 | 0 | 6.6667 | PASS
*KPI Info Only can't be subject for rejection
2024

## Timing Advance
5. Timing Advance
| Timing Advance Distribution | Timing Advance Neighbor Cell (Info Only)
2024
Sector 3 -> 1.1 KM -> 59.59%
Sector 2 -> 3.2 KM -> 100.00%
Sector 1 -> 3.2 KM -> 98.46%
Sector 2 -> 3.2 KM -> 100.00%
Sector 2 -> 1.1 KM -> 61.47%
Sector 3 -> 3.2 KM -> 99.31%

## ATP Document
7. ATP Document Attachment
2024

## Justification
6. Justification
| KPI | Finding Issue |  | Remark
| NMS and VDT already Pass | RSRP improve and CQI improve RSRP Before 40.76%, After 65.37%, Improve 24.61% CQI Before 59.37%, After 74.67%, Improve 15.30%
| RSRP MDT 20^20 |  |  | RSRP MDT 50^50
| CQI MDT 20^20 |  |  | CQI MDT 50^50
MOD 3 Collosion Clear
PCI
Population
TA NPM WEEK34
AC4G18_4214270E_4 |  |  | AC4G18_4214270E_5 |  | AC4G18_4214270E_6

## Optimization Tracker
Activity | [7 empty] | Before | [8 empty] | After | [8 empty] | Parameter Action | Result
[8 empty] | Azimuth |  |  | Mech Tilt |  |  | E Tilt |  |  | Azimuth |  |  | Mech Tilt |  |  | E Tilt
Type of Site | Tower ID | DU ID Father | DU ID Son | RF SOW | Date | Issue | Root Cause | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Macro | SUM-AC-LSM-0131 | SUM-AC-LSM-0131_WLUAL | SUM-AC-LSM-0131_WLUAL_R4T_L1800 | IT & OSS |  |  |  | 140 | 245 | 310 | 4 | 3 | 4 | 2 | 2 | 2 | 50 | 210 | 280 | 3 | 4 | 2 | RET | RET | RET

## INFO
Info
1 | GE 1st Tier | OK |  | ✅
2 | PAYLOAD Cluster | Improve |  | ✅
3 | PAYLOAD Site Level | Improve |  | ✅
4 | PCI Homogen | OK |  | ✅
5 | PRB | SOW Balance |  | ✅
6 | RANK2 | Sector SOW Improve |  | ✅
7 | PORT UNBALANCE | Balance | Info only | ✅
8 | ATP | ATP Approved | Info only | ✅
9 | MR RSRP | #REF! | 21.52% | ✅
10 | MR CQI | #REF! | 78.46% | ✅
11 | TA Overshoot | safe >80% |  | ✅
12 | ALARM | OK |  | ✅
13 | VSWR | Clear |  | ✅
14 | CRS PORT | 4 Port |  | ✅
15 | LICENSE | Clear |  | ✅
16 | PCI MOD3 | Clear |  | ✅
17 | Capture review CO NPM |  |  | ❌
1. RET Info
2. Capture Active Alarm
3. Capture VSWR Setting
4. LTE Bandwidth and MIMO Config
5. Power Info
6. DSP ETHPORT
7. TA ISD
8. All KPI
Payload & User Site Level
Check Point
New Site
Check Point
1. GE 1st Tier ✅ OK
2. PCI HOMOGEN✅ OK
3. PRB ❌ Unbalance Sec 1 & Sec 3
4. RANK2 ✅ Sector SOW Improve > 21.6%
5. PORT ✅ balance (Info Only)
6. ATP ✅ ATP NY Approved (Info Only)
7. MR RSRP ❌ RSRP > -105 dBm 46.84%
8. MR CQI ✅ CQI > 78.46%
9. TA Overshoot ✅ safe >80%
10. ALARM ✅ OK
11. VSWR ✅ clear
12. CRS PORT ✅ 2ports
13. LICENSE ✅ clear
14. PCI MOD3 ✅ OK
15. Capture review CO NPM
Audit
Before
After
Integrasi

## Conclusion & Remarks
8. Conclusion & Remarks
| We Summarize that |  |  |  | 4214270E_LTE_Poltek Lhokseumawe |  |  |  | meets below KPI score:
|  |  |  | KPI Category |  | All | Pass | Fail | Percentage
|  |  |  | Driveless KPI |  | 5 | 4 | 1 | 80%
|  |  |  | NMS KPI |  | 15 | #REF! | #REF! | #REF!
|  | We conclude that |  |  | 4214270E_LTE_Poltek Lhokseumawe |  |  |  | is:
Pass, without note
Pass, without note
Not pass
with remark as follows :
Remarks :
2024